## GanttChart
Gantt Chart |  |  |  | Version 1.7.3 |  | © 2006-2012 Vertex42 LLC |  |  |  | 0
HELP
Flood and Cyclone Early Warning(MERN Stack based app)
| Project Lead: | Md. Hasibul Islam Hemel | [246 empty] | [42]
| Start Date: | 2025-08-19
[42] | [8 empty] | First Day of Week (Mon=2): | 2 | 2025-08-18 | 2025-08-19 | 2025-08-20 | 2025-08-21 | 2025-08-22 | 2025-08-23 | 2025-08-24 | 2025-08-25 | 2025-08-26 | 2025-08-27 | 2025-08-28 | 2025-08-29 | 2025-08-30 | 2025-08-31 | 2025-09-01 | 2025-09-02 | 2025-09-03 | 2025-09-04 | 2025-09-05 | 2025-09-06 | 2025-09-07 | 2025-09-08 | 2025-09-09 | 2025-09-10 | 2025-09-11 | 2025-09-12 | 2025-09-13 | 2025-09-14 | 2025-09-15 | 2025-09-16 | 2025-09-17 | 2025-09-18 | 2025-09-19 | 2025-09-20 | 2025-09-21 | 2025-09-22 | 2025-09-23 | 2025-09-24 | 2025-09-25 | 2025-09-26 | 2025-09-27 | 2025-09-28 | 2025-09-29 | 2025-09-30 | 2025-10-01 | 2025-10-02 | 2025-10-03 | 2025-10-04 | 2025-10-05 | 2025-10-06 | 2025-10-07 | 2025-10-08 | 2025-10-09 | 2025-10-10 | 2025-10-11 | 2025-10-12 | 2025-10-13 | 2025-10-14 | 2025-10-15 | 2025-10-16 | 2025-10-17 | 2025-10-18 | 2025-10-19 | 2025-10-20 | 2025-10-21 | 2025-10-22 | 2025-10-23 | 2025-10-24 | 2025-10-25 | 2025-10-26 | 2025-10-27 | 2025-10-28 | 2025-10-29 | 2025-10-30 | 2025-10-31 | 2025-11-01 | 2025-11-02 | 2025-11-03 | 2025-11-04 | 2025-11-05 | 2025-11-06 | 2025-11-07 | 2025-11-08 | 2025-11-09 | 2025-11-10 | 2025-11-11 | 2025-11-12 | 2025-11-13 | 2025-11-14 | 2025-11-15 | 2025-11-16 | 2025-11-17 | 2025-11-18 | 2025-11-19 | 2025-11-20 | 2025-11-21 | 2025-11-22 | 2025-11-23 | 2025-11-24 | 2025-11-25 | 2025-11-26 | 2025-11-27 | 2025-11-28 | 2025-11-29 | 2025-11-30 | 2025-12-01 | 2025-12-02 | 2025-12-03 | 2025-12-04 | 2025-12-05 | 2025-12-06 | 2025-12-07 | 2025-12-08 | 2025-12-09 | 2025-12-10 | 2025-12-11 | 2025-12-12 | 2025-12-13 | 2025-12-14 | 2025-12-15 | 2025-12-16 | 2025-12-17 | 2025-12-18 | 2025-12-19 | 2025-12-20 | 2025-12-21 | 2025-12-22 | 2025-12-23 | 2025-12-24 | 2025-12-25 | 2025-12-26 | 2025-12-27 | 2025-12-28 | 2025-12-29 | 2025-12-30 | 2025-12-31 | 2026-01-01 | 2026-01-02 | 2026-01-03 | 2026-01-04 | 2026-01-05 | 2026-01-06 | 2026-01-07 | 2026-01-08 | 2026-01-09 | 2026-01-10 | 2026-01-11 | 2026-01-12 | 2026-01-13 | 2026-01-14 | 2026-01-15 | 2026-01-16 | 2026-01-17 | 2026-01-18 | 2026-01-19 | 2026-01-20 | 2026-01-21 | 2026-01-22 | 2026-01-23 | 2026-01-24 | 2026-01-25 | 2026-01-26 | 2026-01-27 | 2026-01-28 | 2026-01-29 | 2026-01-30 | 2026-01-31 | 2026-02-01 | 2026-02-02 | 2026-02-03 | 2026-02-04 | 2026-02-05 | 2026-02-06 | 2026-02-07 | 2026-02-08 | 2026-02-09 | 2026-02-10 | 2026-02-11 | 2026-02-12 | 2026-02-13 | 2026-02-14 | 2026-02-15 | 2026-02-16 | 2026-02-17 | 2026-02-18 | 2026-02-19 | 2026-02-20 | 2026-02-21 | 2026-02-22 | 2026-02-23 | 2026-02-24 | 2026-02-25 | 2026-02-26 | 2026-02-27 | 2026-02-28 | 2026-03-01 | 2026-03-02 | 2026-03-03 | 2026-03-04 | 2026-03-05 | 2026-03-06 | 2026-03-07 | 2026-03-08 | 2026-03-09 | 2026-03-10 | 2026-03-11 | 2026-03-12 | 2026-03-13 | 2026-03-14 | 2026-03-15 | 2026-03-16 | 2026-03-17 | 2026-03-18 | 2026-03-19 | 2026-03-20 | 2026-03-21 | 2026-03-22 | 2026-03-23 | 2026-03-24 | 2026-03-25 | 2026-03-26 | 2026-03-27 | 2026-03-28 | 2026-03-29 | 2026-03-30 | 2026-03-31 | 2026-04-01 | 2026-04-02 | 2026-04-03 | 2026-04-04 | 2026-04-05 | 2026-04-06 | 2026-04-07 | 2026-04-08 | 2026-04-09 | 2026-04-10 | 2026-04-11 | 2026-04-12
WBS | Tasks | Task Lead | Start | End | Duration (Days) | % Complete | Working Days | Days Complete | Days Remaining | 2025-08-18: 2025-08-18; 2025-08-25: 2025-08-25; 2025-09-01: 2025-09-01; 2025-09-08: 2025-09-08; 2025-09-15: 2025-09-15; 2025-09-22: 2025-09-22; 2025-09-29: 2025-09-29; 2025-10-06: 2025-10-06; 2025-10-13: 2025-10-13; 2025-10-20: 2025-10-20; 2025-10-27: 2025-10-27; 2025-11-03: 2025-11-03; 2025-11-10: 2025-11-10; 2025-11-17: 2025-11-17; 2025-11-24: 2025-11-24; 2025-12-01: 2025-12-01; 2025-12-08: 2025-12-08; 2025-12-15: 2025-12-15; 2025-12-22: 2025-12-22; 2025-12-29: 2025-12-29; 2026-01-05: 2026-01-05; 2026-01-12: 2026-01-12; 2026-01-19: 2026-01-19; 2026-01-26: 2026-01-26; 2026-02-02: 2026-02-02; 2026-02-09: 2026-02-09; 2026-02-16: 2026-02-16; 2026-02-23: 2026-02-23; 2026-03-02: 2026-03-02; 2026-03-09: 2026-03-09; 2026-03-16: 2026-03-16; 2026-03-23: 2026-03-23; 2026-03-30: 2026-03-30; 2026-04-06: 2026-04-06
1 | Documentations and Diagrams | Md. Hasibul Islam Hemel | 2025-08-19 | 2025-10-23 |  |  | 48 | 0 | 0
1.1 | SRS Submission |  | 2025-08-19 | 2025-08-21 | 5 |  | 3 | 0 | 5
1.2 | ER Diagram |  | 2025-08-21 | 2025-08-21 | 5 |  | 1 | 0 | 5
1.2.1 | DFD(Level 0) |  | 2025-09-04 | 2025-09-04 | 5 |  | 1 | 0 | 5
1.2.2 | DFD (Level 1) |  | 2025-09-04 | 2025-09-04 | 5 |  | 1 | 0 | 5
1.3 | DFD(Level 2) |  | 2025-09-11 | 2025-09-11 | 5 |  | 1 | 0 | 5
1.4 | Use Case Diagram |  | 2025-09-13 | 2025-09-13 | 5 |  | 0 | 0 | 5
1.5 | Class Diagram |  | 2025-10-09 | 2025-10-09
1.6 | Activity and Sequence Diagram |  | 2025-10-16 | 2025-10-16
2 | Backend Development | Md. Shoyaif Rahman | 2025-08-20 | 2025-09-07 | 8 | 6.25% | 13 | 0 | 8
2.1 | Setup Node.js and Express server |  | 2025-08-20 | 2025-08-22 | 5 | 25% | 3 | 1 | 4
2.2 | Implement user authentication |  | 2025-08-23 | 2025-08-23 | 5 |  | 0 | 0 | 5
2.3 | Develop alert CRUD APIs |  | 2025-08-24 | 2025-08-25 | 5 |  | 1 | 0 | 5
2.4 | Integrate external weather/flood APIs |  | 2025-08-27 | 2025-08-27 | 5 |  | 1 | 0 | 5
2.5 | Handle error logging and validations |  | 2025-09-01 | 2025-09-03
2.6 | Test APIs with Postman |  | 2025-09-05 | 2025-09-07
3 | Frontend Development | Md. Shoyaif Rahman | 2025-09-07 | 2025-09-09 | 3 | 50% | 2 | 1 | 2
3.1 | Setup React project |  | 2025-09-07 | 2025-09-07 | 6 | 50% | 0 | 3 | 3
3.2 | Implement login/signup forms |  | 2025-09-07 | 2025-09-07 | 6 | 50% | 0 | 3 | 3
3.3 | Create dashboard |  | 2025-09-08 | 2025-09-08 | 6 | 50% | 1 | 3 | 3
3.4 | Implement alert details page |  | 2025-09-09 | 2025-09-09 | 6 | 50% | 1 | 3 | 3
3.5 | Integrate notifications UI
3.6 | Implement responsive design
3.7 | Connect frontend with backend APIs
4 | Integration | Md. Shoyaif Rahman | 2024-03-31 | 2024-05-21 | 52 | 0% | 37 | 0 | 52
4.1 | Integrate frontend and backend |  | 2024-03-31 | 2024-04-04 | 5 | 0% | 4 | 0 | 5
4.2 | Test API responses in frontend |  | 2024-04-15 | 2024-04-19 | 5 | 0% | 5 | 0 | 5
4.3 | Implement real-time alert update flow |  | 2024-04-30 | 2024-05-04 | 5 | 0% | 4 | 0 | 5
4.4 | Handle errors and edge cases |  | 2024-05-17 | 2024-05-21 | 5 | 0% | 3 | 0 | 5
5 | Testing | Md. Shoyaif Rahman | 2024-02-27 | 2024-03-03 | 6 | 50% | 4 | 3 | 3
5.1 | Unit testing |  | 2024-02-27 | 2024-03-03 | 6 | 50% | 4 | 3 | 3
5.2 | Integration testing
5.3 | User acceptance testing
5.4 | Performance testing
5.5 | Bug fixing and optimization
TEMPLATE ROWS: Copy and insert the entire section, or just the specific sub tasks, depending on which level you want to use (formulas are different for different WBS levels)
1 | Task Category 1 |  | 2009-01-05 | 2009-01-05 | 1 | 0% | 1 | 0 | 1
1.1 | Sub Task level 2 |  | 2009-01-05 | 2009-01-05 | 1 | 0% | 1 | 0 | 1
1.1.1 | Level 3 Task |  | 2009-01-05 | 2009-01-05 | 1 | 0% | 1 | 0 | 1
1.1.1.1 | Level 4 task |  | 2009-01-05 | 2009-01-05 | 1 | 0% | 1 | 0 | 1
To unlock this spreadsheet, purchase Gantt Chart Template Pro: http://www.vertex42.com/ExcelTemplates/excel-gantt-chart.html

## © (hidden)
Gantt Chart Template
© 2008-2009 Vertex42 LLC
http://www.vertex42.com/ExcelTemplates/excel-gantt-chart.html

## GanttChartPro
Gantt Chart Template Pro
Gantt Chart Template Pro is similar to this free version,
but it is unlocked, more feature-packed, and includes other
bonus content such as sample project schedules.
Already spent a lot of time working with this free version?
That's okay. In addition to downloading the Gantt Chart Template Pro
files, you will be given the password for unlocking this spreadsheet.
Learn More About Gantt Chart Template Pro
http://www.vertex42.com/ExcelTemplates/excel-gantt-chart.html
- View screenshots
- Watch demo videos
Benefits and Features of Gantt Chart Template Pro
Unlocked (worksheets are not password-protected)
By unlocking the free version or using Gantt Chart Template Pro, you will be able to use
all of the functions and features available in Excel, such as formatting cells, inserting
columns, and grouping rows.
More Ways to Define a Task
Choose from a larger set of template rows that provide more options for
defining the Start date, End date, duration, and dependency of tasks.
Define a task based on the …
- Start date and End date
- Start date and Work days
- Start date and Calendar days
- Predecessor and End date
- Predecessor and Work days
- Predecessor and Calendar days
Easily Create Task Dependencies
Though you can still use your own formulas for creating task dependencies,
the new Predecessor options make it very simple. One of the demo videos
discusses this in detail.
Exclude Holidays from Work Days
List holidays in a separate sheet that you want to exclude from work days.
Sample Project Schedules
To get a head start on defining your project schedule, you can use
one of the 3 sample gantt charts:
- Home Construction Project Schedule
- Custom Software Project Schedule
- Website Development Project Schedule
New Excel 2007+ Version (XLSX)
In addition to Gantt Chart Template Pro for Excel 2003, you will be able to download
an XLSX version, for Excel 2007 or later, that allows you to easily color-code the
bars of the gantt chart.
Learn More About Gantt Chart Template Pro

## TermsOfUse
Terms of Use
© 2006 - 2012 Vertex42 LLC. All rights reserved.
This template is considered a copyrighted work under the Unites States and other copyright laws and is the property of Vertex42 LLC. The items listed below are additional points to help clarify how you may use this template.
Not for Resale or Public Sharing
You may make archival copies and customize this template only for your personal use or use within your company or organization and not for resale or public sharing.
You may not remove or alter any logo, trademark, copyright, disclaimer, brand, terms of use, attribution, or other proprietary notices or marks within this template.
This template and any customized or modified version of this template may NOT be sold, distributed, published to an online gallery, hosted on a website, or placed on a public server.
Limited Private Sharing
Provided that you observe the above terms, you may share your edited version of this template *privately* with those specific people who **require** access to it within your immediate family, organization, or company.
* "Privately" means only accessible to those few people who you expressively give permission to view or edit your file. It is your responsibility to ensure that adequate security measures are used so that your file is not available to the public.
** Examples of acceptable private sharing with people who "require access" may include (a) sharing a budget spreadsheet with a spouse, (b) sharing a project schedule with your project team, or (c) sharing a timesheet with your employee or manager.
See the following page on Vertex42.com for the complete license agreement and examples of other allowed uses:
http://www.vertex42.com/licensing/EULA_privateuse.html
Disclaimer
This template is provided for informational or educational use only and is not intended to be relied on as medical, financial, legal, or other professional advice.
Vertex42 LLC makes no guarantee or representations about this template, or the accuracy or completeness of the content contained within this template.
Vertex42 LLC encourages you to seek the aid of a qualified professional before making decisions regarding health, financial, or legal issues.